Marine Research Plan Workplan: as at 27 September 2013

| Activity | Planed timeline | Actual date | Venue |
| --- | --- | --- | --- |
| Research strategy workshop |  | 26 September 2013 | Pretoria |
| NRF/DST update meeting |  | 27 September 2013 | Pretoria |
| Task Team meeting 1 | October 2013 (week 1) |  |  |
| Working Group meeting 1 | October 2013 (week 2) |  |  |
| Working group submission 1 | October 2013 (week 4) |  |  |
| NRF/DST update meeting | October 2013 (week 4) |  | Pretoria |
| Task Team meeting 2 | November 2013 (week 2) |  |  |
| Working Group meeting 2 | November 2013 (week 2) |  |  |
| Working group submission 2 | November 2013 (week 4) |  |  |
| NRF/DST update meeting | November 2013 (week 4) |  | Pretoria |
| Draft document submission | December 2013 (week 1) |  |  |
| Stakeholder Feedback | December 2013 (week 1+ 2) |  |  |
| Writer present final draft to DST/NRF | December 2013 (week 2) | 13 December 2013 |  |
| DST internal processes | December 2013 - February 2014 |  |  |
|  | March 2014 (week 3) | 21 March 2014 | Pretoria |
| Stakeholder Feedback Meeting | March 2014 (week 4) |  | Pretoria |

Task Team:		Working group convener x 3; working group writer x 3; Lead 				writer x 1; DST staff x 2; NRF staff x 2.

Working Group:  	Convener x 1; writer x 1; participants x 8